## Project tracker
Project Task Tracker |  |  |  | Percent over/under to highlighted numbers | 25%
Task | Category | Assigned to | Estimated start | Estimated finish | Estimated work (in hours) | Estimated duration (in days) | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes
Connect 4 Coding | Coding | Student 1 | 2024-10-30 | 2024-11-03 | 5 | 3 | 2024-10-31 | 2024-11-02 | 5 | 2 | completed the code for connect4 in addition to a rough gui outline to test it out
Connect 4 Use Case descriptions | Documentation | Student 1 | 2024-11-02 | 2024-11-03 | 3 | 1 | 2024-11-01 | 2024-11-02 | 3 | 1 | use case descriptions for connect4 completed
Class structure diagram | Documentation | Student 1 | 2024-11-03 | 2024-11-03 | 2 | 0 | 2024-11-03 | 2024-11-03 | 2 | 0 | one general class structure diagram completed
Checkers Coding | Coding | Student 2 | 2024-11-02 | 2024-11-04 | 8.75 | 2 | 2024-11-02 | 2024-11-04 | 8.75 | 2
Checkers Use case descriptions | Documentation | Student 2 | 2024-11-01 | 2024-11-02 | 1.5 | 1 | 2024-11-01 | 2024-11-02 | 1.8 | 1 | Completed the use case descriptions for Move a piece, Move a king, and Start Game. Also worked on the use case diagram
Checkers Initial Coding | Coding | Student 3 | 2024-11-02 | 2024-11-02 | 3 | 1 | 2024-11-02 | 2024-11-02 | 4 | 1 | Worked on the code for Checkers game.
Checkers Use Case Descriptions/Diagrams | Documentation | Student 3 | 2024-11-02 | 2024-11-02 | 3 | 1 | 2024-11-02 | 2024-11-02 | 4 | 1 | Completed a rough draft of the use case descriptions and diagrams.
Tic Tac Toe Use Case Diagram | Documentation | Student 4 | 2024-11-02 | 2024-11-03 | 2 | 1 | 2024-11-03 | 2024-11-04 | 1 | 2 | Completed use case diagram for Tic Tac Toe based off completed use cases
Connect 4 Use Case Diagram | Documentation | Student 4 | 2024-11-02 | 2024-11-03 | 1.5 | 1 | 2024-11-03 | 2024-11-04 | 1.5 | 1 | Completed use case diagram for Connect 4 based off completed use cases
Tic Tac Toe Coding | Coding | Student 5 | 2024-11-02 | 2024-11-03 | 4 | 1 | 2024-11-02 | 2024-11-03 | 6 | 1 | Start and complete the code for Tic Tac Toe
Tic Tac Toe use case descriptions | Documentation | Student 5 | 2024-11-02 | 2024-11-04 | 2 | 1 | 2024-11-02 | 2024-11-03 | 4 |  | Start and complete the case descriptions for Tic Tac Toe
SETUP

## Task Lookup
Task Number | Task Name | Task Description
Task 1 | coding
Task 2 | use case descriptions
Task 3 | use case diagrams
Task 4 | class structure diagram

## Setup
Setup
Category Name | Employee Name
Category 1 | Student 1
Category 2 | Student 2
Category 3 | Student 3
Category 4 | Student 4
Category 5 | Student 5
Category 6 | Student 6
PROJECTS