## Project tracker
Project Task Tracker |  |  |  | Percent over/under to highlighted numbers | 25%
Task | Category | Assigned to | Estimated start | Estimated finish | Estimated work (in hours) | Estimated duration (in days) | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes
Chat use case desc | Planning |  | 2024-10-28 | 2024-11-04 | 0.5 | 6 | 2024-11-04 | 2024-11-04 | 0.75 | 0 | finished Chat description
Overall planning for whats needed for networking - placed in a document | Planning |  | 2024-10-30 | 2024-10-30 | 2 | 1 | 2024-10-30 | 2024-10-30 | 2.75 | 1 | Outline finished
Structure diagram planning | Planning |  | 2024-10-29 | 2024-10-30 | 3 | 1 | 2024-10-30 | 2024-10-31 | 3 | 2 | SD outline setup
Networking Reaserch | Planning |  | 2024-10-30 | 2024-10-30 | 1 | 1 | 2024-11-01 | 2024-11-03 | 3 | 2 | supplimentary networking research
Structure diagram | Planning |  | 2024-10-29 | 2024-11-01 | 5 | 2 | 2024-10-29 | 2024-11-01 | 7 | 2 | SD design completion
Seqence Diagram | Planning |  | 2024-10-31 | 2024-10-31 | 1 | 0 | 2024-10-31 | 2024-10-31 | 2 | 0
Create Base Classes for coding | Coding |  | 2024-11-04 | 2024-11-04 | 1 | 0 | 2024-11-04 | 2024-11-04 | 1 | 0
Network Class | Coding |  | 2024-11-04 | 2024-11-20 | 5 | 16
AuthenticationHandler | Coding |  | 2024-11-04 | 2024-11-12 | 3 | 8
ChatManager | Coding |  | 2024-11-04 | 2024-11-08 | 3 | 4
GameSyncManager | Coding |  | 2024-11-04 | 2024-11-14 | 3 | 10
LeaderboardHandler | Coding |  | 2024-11-04 | 2024-11-19 | 2 | 15
ServerRelay | Coding |  | 2024-11-04 | 2024-11-30 | 7 | 26
SETUP

## Task Lookup
Task Number | Task Name | Task Description
Task 1
Task 2
Task 3

## Setup
Setup
Category Name | Employee Name
Planning | Student 1
Coding | Student 2
Category 3 | Student 3
Category 4 | Student 4
Category 5 | Student 5
PROJECTS