## Project tracker
Project Task Tracker |  |  |  | Percent over/under to highlighted numbers | 25%
Task | Assigned to | Estimated start | Estimated finish | Estimated work (in hours) | Estimated duration (in days) | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes
Placement Test Use Case | Student 1 | 2024-10-30 | 2024-11-04 | 3 | 4 | 2024-10-30 | 2024-11-04 | 3 | 4 | Finished the Placement Test Use Case for the description and diagram
Placement Test Structure Diagram | Student 1 | 2024-11-01 | 2024-11-04 | 1 | 3 | 2024-11-01 | 2024-11-04 | 2 | 3 | Created the PlacementTest class and its part of the structure diagram with the methods that will be used for it
Adjust Rating Use Case | Student 2 | 2024-11-09 | 2024-11-09 | 1 | 0 | 2024-11-09 | 2024-11-09 | 1 | 1 | Wrote out the use case description for Adjust Rating
Adjust Rating Class and Diagrams | Student 2 | 2024-11-10 | 2024-11-10 | 3 | 0 | 2024-11-10 | 2024-11-10 | 5 | 1 | Created the AdjustRating class and its methods and added them to the use case and structure diagrams
Matchmake Use Case | Student 3 | 2024-11-01 | 2024-11-04 | 1 | 1 | 2024-11-04 | 2024-11-04 | 0.17 | 1
Matchmake Structure Diagram | Student 3 | 2024-11-01 | 2024-11-04 | 1 | 1 | 2024-11-04 | 2024-11-04 | 0.1 | 1
Matchmake Class Code | Student 3 | 2024-11-01 | 2024-11-03 | 2 | 2 | 2024-11-03 | 2024-11-03 | 1 | 1
SETUP
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The tracker is missing the category section that describes the kind of work being done during each task (Planning, documentation, coding, etc)
Note on G7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Student 2’s estimated work duration in days is formatted a bit weird. The minimum duration in days should be 1, so I assume that’s what the student meant, but it would be better to list it as 1 instead of 0 for consistency and organization. Not a big deal though
Note on D9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Student 3’s estimated start and finish date for their tasks doesn’t match the estimated duration in days. This should be changed so that the expected start and finish dates should better align with the estimated duration
Note on H9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: According to the actual start dates, Student 3 started late, beginning on the day of the deadline. While the workload was less than expected and the deadline was met, this could be a sign of procrastination or rushed inadequate work and should be addressed to see if the late start was the cause of student 3’s work ethic, a mistake in forgetting to adjust the expected start dates (as they don’t match the expected duration in days), or external matters.
Note on L9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Student 3’s tasks have no notes. It would be helpful to have them to describe the tasks that student 3 has done and better track the overall state and progress of the project
Note on H11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It seems Student 3 started work on the code before making the use case descriptions and structure diagram. It would be better to do these in reverse order to better structure the code before making it.

## Task Lookup
Task Number | Task Name | Task Description
Task 1
Task 2
Task 3
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Task lookup page incomplete

## Setup
Setup
Category Name | Employee Name
Category 1 | Jessica Truong
Category 2 | Saif Farag
Category 3 | Student 3
Category 4 | Student 4
Category 5 | Student 5
Category 6 | Student 6
PROJECTS
Note on C7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Only two students are named and the categories aren’t listed