## Project tracker
Project Task Tracker |  |  |  | Percent over/under to highlighted numbers | 25%
Task | Category | Assigned to | Estimated start | Estimated finish | Estimated work (in hours) | Estimated duration (in days) | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes
usecase diagram & description | planning | Student 6 | 2024-11-08 | 2024-11-13 | 10 | 5 | 2024-11-08 | 2024-11-13 | 5 | 5 | Finished use case description
class structure diagram | planning | Student 6 | 2024-11-08 | 2024-11-18 | 4 | 10 | 2024-11-08 | 2024-11-18 | 6 | 10 | Finshed use case diagram
gui screen containing login, reg, home page | planning | Student 6 | 2024-11-13 | 2024-11-30 | 50 | 17 | 2024-11-13 | 2024-11-30 | 4 | 17 | Finished class structure diagram
GUI character and board designs | coding | Student 5 | 2024-11-13 | 2024-11-30 | 15 | 17 | 2024-11-13 | 2024-11-30 | 1 | 17 | Finished a sample of the login page
chatbox and arena | coding | Student 5 | 2024-11-13 | 2024-11-30 | 10 | 17 | 2024-11-13 | 2024-11-30 | 1 | 17 | Working on linking login page together and testing
scoreboard implemented for all games | coding | Student 5 | 2024-11-16 | 2024-11-30 | 5 | 14 | 2024-11-16 | 2024-11-30 | 6 | 14 | Working on logo creation for the game
SETUP
Note on D5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assigning all the planning to one student/group and all the coding to another is not a great idea because there won’t be someone with a great understanding of the plan working on and overlooking the coding process who can ensure that it accurately follows the initial plan. i.e there won’t be great communication and coordination between the coding and planning sides of the project, hence greater chance for errors, problems, and poorly structured code later on
Note on M5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Student 6 could add a bit of detail to the task notes, better describing the work they did. Ex which use case description did they finish, what did they add to the diagrams in order to finish them, what classes/functions are the descriptions and diagrams for, etc
Note on H6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The estimated duration in days and hours for tasks 2-6 suggest that they are rather large and would probably be able to be split among multiple individuals rather than just Student 5 and 6. i.e It might’ve been a good idea to split these tasks among more people if possible
Note on K7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Certain tasks get finished within 1-4 hours of work but is spread out between several weeks. This is very strange, and the students who did these tasks should clarify the low work hours compared to long duration in days. If the issue is simply neglecting to record the actual days taken and simply copy/pasting the estimated duration, then it should simply be changed to reflect the actual time taken.
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Student 5’s tasks don’t seem to reflect the work described on the task notes. It would be better to separate the unrelated work and list it as a separate task for better documentation, and mention the work related most to the task in the notes; or to reword the task notes to better match the task
Note on M9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Student 5’s task notes imply that they did not finish the tasks and are actively working on them. Either change the wording, or don’t list them as completed.

## Task Lookup
Task Number | Task Name | Task Description | making logo
Task 1
Task 2
Task 3
Note on D1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Task lookup page incomplete

## Setup
Setup
Category Name | Employee Name
planning | student 1
coding | student 2
design | student 3
Category 4 | student 4
Category 5 | student 5
Category 6 | Student 6
PROJECTS
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No students were named and no tasks regarding design were done. Not necessarily a bad thing but if there were no tasks related to design to begin with, it maybe shouldn’t be listed as a category here