project_tracker_networking

Issues Identified

The issues identified are in terms of any kind of timing mismanagement, missed milestones or any unrealistic deadlines that were set. Also highlighting any potential risks that could have impacted the successful completion of the first iteration (e.g - dependencies between tasks, resource allocation issues). At the end it also contains suggestions for improving the timeline or rearrangement of the tasks to mitigate risks.

### Timing Issues

1. For the task “Structure diagram planning”

- Estimated Finish: 2024-10-30  	- Actual Finish: 2024-10-31

- Estimated Duration: 1 day       	- Actual Duration: 2 days

This indicates a minor delay in the planning and was completed one day later than expected.

2. For the task “Networking Research”

- Estimated Finish: 2024-10-30  		- Actual Finish: 2024-11-03

- Estimated Duration: 1 day       		- Actual Duration: 2 days

This task was delayed by 3 days which is probably because of the additional time taken for research. Hence, this task should have been prioritized first and could have been scheduled initially.

### Potential Risks

1. Delays in the planning of the structure diagram and the networking research could have caused delaying of other dependent tasks and thereby leading to delayed completion of the upcoming tasks.

2. There wasn’t clear indication of the person responsible for each individual task as well, which would later lead to improper distribution and allocation of resources.

3. The tasks that were mentioned that missed their deadlines were estimated to take only a day but eventually got delayed which indicates original estimation might not have been enough for the task and could have added a buffer time.

4. Being more specific, it seems you intend to have LeaderboardHandler and ChatManager completed before ServerRelay. Please acknowledge that the first two will not work without the last one, so maybe reconsider your priorities for estimated dates.

### Suggestions:

1. One of the suggestions would be to even further breakdown the tasks into smaller ones that are manageable and achievable.

2. Add buffer time between dependent tasks so that if there’s any delay in the previous task due to unforeseen circumstances, it won’t at least affect the overall timeline for the submission.

3. "Being more specific with the previous suggestion, consider breaking down your Diagram tasks into more specific ones (i.e. instead of having a task called "Structure Diagram", create one named AuthenticationClass Structure Diagram Representation"). When you have a very generic task such as "Structure Diagram", important details are lost, and planning gets harder.

- For instance, in your instance of SD, the only indication of progress is "SD Design completion", but what does this even entail? Considering this is seven hours of work, you ideally need to have more detailed descriptions of what has been accomplished during this long period (i.e. Who completed the Server Relay representation? When did they do it? What is their feedback on it?)"

4. Also, proper indication of assigned members for the task should be mentioned.

5. As you have different trackers for certain aspects of your project, consider adding your networking sub team members in the "Setup" section

6. Time was allotted for creating sequence diagrams. However, there was no need for that as sequence diagrams weren't a part of the submission for Iteration 1. Thereby, the time allotted could have been used for any other important task.

7. It’s better to prioritize tasks properly and set proper deadlines for them such as research tasks where it would naturally take a longer time or something in terms of planning.

8. (Extra): Consider also tracking your discussion and feedback meetings, as well as your scrums. Not necessary, but a good addition for more organization