## Project tracker
Project Task Tracker |  |  |  | Percent over/under to highlighted numbers | 25%
Task | Category | Assigned to | Estimated start | Estimated finish | Estimated work (in hours) | Estimated duration (in days) | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes
Connect 4 Coding | Coding | Student 1 | 2024-10-30 | 2024-11-03 | 5 | 3 | 2024-10-31 | 2024-11-02 | 5 | 2 | completed the code for connect4 in addition to a rough gui outline to test it out
Connect 4 Use Case descriptions | Documentation | Student 1 | 2024-11-02 | 2024-11-03 | 3 | 1 | 2024-11-01 | 2024-11-02 | 3 | 1 | use case descriptions for connect4 completed
Class structure diagram | Documentation | Student 1 | 2024-11-03 | 2024-11-03 | 2 | 0 | 2024-11-03 | 2024-11-03 | 2 | 0 | one general class structure diagram completed
Checkers Coding | Coding | Student 2 | 2024-11-02 | 2024-11-04 | 8.75 | 2 | 2024-11-02 | 2024-11-04 | 8.75 | 2
Checkers Use case descriptions | Documentation | Student 2 | 2024-11-01 | 2024-11-02 | 1.5 | 1 | 2024-11-01 | 2024-11-02 | 1.8 | 1 | Completed the use case descriptions for Move a piece, Move a king, and Start Game. Also worked on the use case diagram
Checkers Initial Coding | Coding | Student 3 | 2024-11-02 | 2024-11-02 | 3 | 1 | 2024-11-02 | 2024-11-02 | 4 | 1 | Worked on the code for Checkers game.
Checkers Use Case Descriptions/Diagrams | Documentation | Student 3 | 2024-11-02 | 2024-11-02 | 3 | 1 | 2024-11-02 | 2024-11-02 | 4 | 1 | Completed a rough draft of the use case descriptions and diagrams.
Tic Tac Toe Use Case Diagram | Documentation | Student 4 | 2024-11-02 | 2024-11-03 | 2 | 1 | 2024-11-03 | 2024-11-04 | 1 | 2 | Completed use case diagram for Tic Tac Toe based off completed use cases
Connect 4 Use Case Diagram | Documentation | Student 4 | 2024-11-02 | 2024-11-03 | 1.5 | 1 | 2024-11-03 | 2024-11-04 | 1.5 | 1 | Completed use case diagram for Connect 4 based off completed use cases
Tic Tac Toe Coding | Coding | Student 5 | 2024-11-02 | 2024-11-03 | 4 | 1 | 2024-11-02 | 2024-11-03 | 6 | 1 | Start and complete the code for Tic Tac Toe
Tic Tac Toe use case descriptions | Documentation | Student 5 | 2024-11-02 | 2024-11-04 | 2 | 1 | 2024-11-02 | 2024-11-03 | 4 | 1 | Start and complete the case descriptions for Tic Tac Toe
SETUP
Note on J2: [Positive Feedback] All of your coding tasks have modelling completed beforehand. Well done!
Note on K2: [Positive Feedback] Very well organized. Your estimated dates and hours match your actual duration almost perfectly.
Note on D4: [Suggestion/Potential Risk] Your team leads must keep track of what each member is working on, at any point in time. It is essential for you to track progress, get feedback and allocate resources efficiently.
Note on B6: This is not necessarily a bad approach in this case, but reconsider breaking down your tasks even more in the future. For instance, instead of assigning "Connect 4 Use Case Descriptions" to someone, you could instead assign "Connect 4 Check-for-Win"
Note on K7: It seems you've only taken two hours in developping the model for your structure diagram. Please acknowledge that, even though "volatile", thiese are essential for you to have a basic idea of the interactions and structures of the main classes in your code. For future reference, consider allocating more time for this task.
Note on N8: You present good descriptions in your notes, but make sure to always fill them in, even when it sounds basic or redundant This will help your team overviewers in analyzing the progress this subteam has made in future iterations

## Task Lookup
Task Number | Task Name | Task Description
Task 1 | coding
Task 2 | use case descriptions
Task 3 | use case diagrams
Task 4 | class structure diagram

## Setup
Setup
Category Name | Employee Name
Category 1 | Student 1
Category 2 | Student 2
Category 3 | Student 3
Category 4 | Student 4
Category 5 | Student 5
Category 6 | Student 6
PROJECTS