## Project Tracker
Project Task Tracker |  |  |  | Percent over/under to highlighted numbers | 0%
Task | Category | Assigned to | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes (credit also applies to:)
IGameHandler - structure diagram | Document | Alan Bach | 2024-10-30 | 2024-10-30 | 1 | 0
Start Game - use case description | Document | Elizabeth Akinpelu | 2024-10-31 | 2024-10-31 | 1 | 0 | Alan Bach, Anmoldeep Gill, Ethan Braum
Game Handler - structure diagram | Document | Alan Bach | 2024-10-30 | 2024-10-30 | 1 | 0
Choose A Side - use case description | Document | Victoria Piquer | 2024-10-30 | 2024-10-31 | 1 | 0 | Alan Bach
Resign Game - use case description | Document | Victoria Piquer | 2024-10-30 | 2024-10-30 | 1 | 0 | Alan Bach
Place A Piece - use case description | Document | Anmoldeep Gill | 2024-10-30 | 2024-10-30 | 1 | 0 | Alan Bach, Ethan Barum
GameBoard - structure diagram | Document | Gabriel Moises | 2024-10-30 | 2024-10-30 | 1 | 0 | Alan Bach
Tic Tac Toe - use case description | Document | Tanisha Mattapalli | 2024-11-02 | 2024-11-03 | 1 | 1 | Richard Nguyen
Player Profile - use case description | Document | Michelle Yoon | 2024-11-03 | 2024-11-03 | 1 | 0 | Richard Nguyen
Checkers Piece - structure diagram | Document | Orest Sinani | 2024-11-03 | 2024-11-03 | 1 | 0 | Alan Bach
Frontend - structure diagram | Document | Richard Nguyen | 2024-11-03 | 2024-11-03 | 1 | 0
Frontend - use case diagram | Document | Richard Nguyen | 2024-11-03 | 2024-11-03 | 1 | 0 | Michelle Yoon, Amir Khan
Connect 4 - use case description | Document | Richard Nguyen | 2024-11-03 | 2024-11-03 | 1 | 0
Tic Tac Toe Piece - structure diagram | Document | Orest Sinani | 2024-11-03 | 2024-11-03 | 1 | 0 | Alan Bach
Connect 4 Piece - structure diagram | Document | Orest Sinani | 2024-11-03 | 2024-11-03 | 1 | 0 | Gabriel Moises, Alan Bach
Checkers Check for Capture - use case description | Document | Victoria Piquer | 2024-11-02 | 2024-11-03 | 1 | 1 | Alan Bach
Check Game End - sequence diagram | Document | Mostafa Abdelazim | 2024-10-31 | 2024-11-03 | 1 | 3
Backend - use case diagram | Document | Lisa Tatarnikov | 2024-10-31 | 2024-11-03 | 1 | 3 | Alan Bach
Aftermath - use case description | Document | Amir Khan | 2024-11-01 | 2024-11-01 | 1 | 0 | Richard Nguyen
Checkers - use case description | Document | Sharon Wong | 2024-10-30 | 2024-11-03 | 1 | 3 | Richard Nguyen
Leaderboard - use case description | Document | Alan Bach | 2024-10-29 | 2024-11-03 | 2 | 4 | Rishabh Agarwal, Richard Nguyen, Mohammad Moustaqim
Login/Sign Out - use case diagram | Document | Natesh Oad | 2024-10-29 | 2024-11-02 | 1 | 3 | Richard Nguyen
Update Player Timer - use case description | Document | Mostafa Abdelazim | 2024-11-01 | 2024-11-02 | 1 | 1 | Alan Bach, Gabriel Moises
Check Game End - use case description | Document | Anmoldeep Gill | 2024-10-31 | 2024-11-02 | 1 | 2 | Alan Bach
Connect 4 Handler - structure diagram | Document | Alan Bach | 2024-10-31 | 2024-11-01 | 1 | 1
Validate Move - use case description | Document | Anmoldeep Gill | 2024-10-31 | 2024-11-02 | 1 | 2 | Alan Bach
Tic Tac Toe Handler - structure diagram | Document | Alan Bach | 2024-10-31 | 2024-11-01 | 1 | 1
Connect 4 Queue - use case diagram | Document | Mohammad Moustaqim | 2024-11-01 | 2024-11-03 | 4 | 2
Checkers Handler - structure diagram | Document | Alan Bach | 2024-10-31 | 2024-11-01 | 1 | 1
Game Piece - structure diagram | Document | Kyle Salazar | 2024-10-31 | 2024-11-01 | 1 | 1
SETUP

## Meeting Records
Meeting Purpose | Team Involved | Meeting Date | Meeting Duration (hours)
Initial Team Meeting | All Members | 2024-10-28 | 1:00
Initial Subteam Meeting | Network Team | 2024-10-29 | 1:00
Initial Subteam Meeting | Backend Team | 2024-10-29 | 1:00
Initial Subteam Meeting | Frontend Team | 2024-10-29 | 1:00
SCRUM | Network Team | 2024-10-31 | 1:00
SCRUM | Backend team | 2024-10-31 | 1:00
SCRUM | Lead Team | 2024-11-02 | 0:30
SCRUM | Frontend Team | 2024-11-03 | 1:00
Compilation Meeting | Lead Team | 2024-11-03 | 1:00
P2 Planning | Lead Team | 2024-11-08 | 1:00

## Timeline
Milestones | Planned Start | Planned Completed | Actual Start | Actual Completed
Complete classes in the class structure diagram | 2024-11-05 | 2024-11-22
Complete first game | 2024-11-05 | 2024-11-09
Complete second game | 2024-11-09 | 2024-11-14
Complete third game | 2024-11-14 | 2024-11-19
Complete feedback for Delta and Echo team | 2024-11-08 | 2024-11-12
Complete letter and submit P2 | 2024-11-12 | 2024-11-13
Profile GUI | 2024-11-06 | 2024-11-22
Complete networking stubs | 2024-11-10 | 2024-11-15
Finalize leaderboard and matchmaking logic | 2024-11-19 | 2024-11-22
Unit testing | 2024-11-15 | 2024-11-24
Change classes according to P2 feedback | 2024-11-18 | 2024-11-22
Integrate project from different teams | 2024-11-23 | 2024-11-25
Documentation for integration created | 2024-11-23 | 2024-11-26
Integration testing | 2024-11-23 | 2024-11-25
Produce gitlog file | 2024-12-04 | 2024-12-04
Record group presentation video | 2024-12-04 | 2024-12-04

## Setup
Setup
Category Name | Employee Name
Plan | Rishabh Agarwal
Design | Sam Safe
Code | Victoria Piquer
Document | Tanisha Mattapalli
Bugfix | Sharon Wong
Test | Samuel Ergando
Richard Nguyen
Orest Sinani
Nathan Phan
Natesh Oad
Mostafa Abdelazim
Morteza Faraji
Mohammad Moustaqim
Michelle Yoon
Lisa Tatarnikov
Kyle Salazar
Hassan Alvi
Hannah Xia
Gabriel Moises
Ethan Braum
Elizabeth Akinpelu
Anmoldeep Gill
Aniruddha Khan
Amir Khan
Alan Bach
PROJECTS