## Project Tracker
Project Task Tracker |  |  |  | Percent over/under to highlighted numbers | 0%
Task | Category | Assigned to | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes
IGameHandler - structure diagram | Document | Alan Bach | 2024-10-30 | 2024-10-30 | 1 | 0
Start Game - use case description | Document | Elizabeth Akinpelu | 2024-10-31 | 2024-10-31 | 1 | 0 | Alan Bach, Anmoldeep Gill, Ethan Braum credited with the same task
Game Handler - structure diagram | Document | Alan Bach | 2024-10-30 | 2024-10-30 | 1 | 0
Choose A Side - use case description | Document | Victoria Piquer | 2024-10-30 | 2024-10-31 | 1 | 0 | Alan Bach credited with the same task
Resign Game - use case description | Document | Victoria Piquer | 2024-10-30 | 2024-10-30 | 1 | 0 | Alan Bach credited with the same task
Place A Piece - use case description | Document | Anmoldeep Gill | 2024-10-30 | 2024-10-30 | 1 | 0 | Alan Bach, Ethan Barum credited with the same task
GameBoard - structure diagram | Document | Gabriel Moises | 2024-10-30 | 2024-10-30 | 1 | 0 | Alan Bach credited with the same task
SETUP

## Meeting Records
Meeting Purpose | Team Involved | Meeting Date | Meeting Duration (hours)
Initial Team Meeting | All Members | 2024-10-28 | 1:00
Initial Subteam Meeting | Network Team | 2024-10-29 | 1:00
Initial Subteam Meeting | Backend Team | 2024-10-29 | 1:00
Initial Subteam Meeting | Frontend Team | 2024-10-29 | 1:00
SCRUM | Network Team | 2024-10-31 | 1:00
SCRUM | Backend team | 2024-10-31 | 1:00

## Setup
Setup
Category Name | Employee Name
Plan | Rishabh Agarwal
Design | Sam Safe
Code | Victoria Piquer
Document | Tanisha Mattapalli
Bugfix | Sharon Wong
Test | Samuel Ergando
Richard Nguyen
Orest Sinani
Nathan Phan
Natesh Oad
Mostafa Abdelazim
Morteza Faraji
Mohammad Moustaqim
Michelle Yoon
Lisa Tatarnikov
Kyle Salazar
Hassan Alvi
Hannah Xia
Gabriel Moises
Ethan Braum
Elizabeth Akinpelu
Anmoldeep Gill
Aniruddha Khan
Amir Khan
Alan Bach
PROJECTS