## Project tracker
Project tracker |  |  |  | Percent over/under to highlighted numbers | 25%
Project | Category | Assigned to | Estimated start | Estimated finish | Estimated work (in hours) | Estimated duration (in days) | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes
Profile Class | Coding | Student 1 | 2024-11-08 | 2024-11-18 |  | 10
User Class | Coding | Student 2 | 2024-11-08 | 2024-11-22 |  | 14
UserStats Class | Coding | Student 3 | 2024-11-07 | 2024-11-24 |  | 17
GameHistory Class | Coding | Student 3 | 2024-11-07 | 2024-11-24 |  | 17
Record Class | Coding | Student 4 | 2024-11-07 | 2024-11-15 |  | 8
AuthService Class | Coding | Student 4 | 2024-11-11 | 2024-11-20 |  | 9
EmailService Class | Coding | Student 5 | 2024-11-11 | 2024-11-20 |  | 9
Test Profile | Testing | Student 1 | 2024-11-15 | 2024-11-18 |  | 3
Test User | Testing | Student 2 | 2024-11-11 | 2024-11-28 |  | 17
Test UserStats | Testing | Student 3 | 2024-11-17 | 2024-11-30 |  | 13
Test GameHistory | Testing | Student 5 | 2024-11-11 | 2024-11-20 |  | 9
Test Record | Testing | Student 4 | 2024-11-17 | 2024-11-25 |  | 8
Test AuthService | Testing | Student 4 | 2024-11-23 | 2024-11-29 |  | 6
Test EmailService | Testing | Student 5 | 2024-11-11 | 2024-11-20 |  | 9
SETUP
Note on E2: Suggestion: Consider having a new page tracking your meetings and what progress has been made up to that meeting
Note on B4: I don't see any type of structure, sequence, or any type of Diagrams/models for your coding tasks. Have you spent time modelling how these methods should function?
Note on G4: Your Tracker is not calculating your Estimated work hours automatically. Refer to previous versions of the tracker document to reinstate it
Note on D5: Remember to assign your tasks to clear assignees. You can use the "Setup" page for more convenience

## Setup
Setup
Category Name | Student Name
Coding | Student 1
Testing | Student 2
Student 3
Student 4
Student 5
PROJECTS